## VCP Format Review
VCP Format Review (01-09-2026)
Key Decisions / Outcomes
1 | VCP reviews will shift from action tracking in Excel to an outcome-oriented format that clearly links actions to business metrics and measurable impact.
2 | A standardized review framework will connect actions, KPIs, enablers, and business impact directly, making it easier for leadership to assess value creation.
3 | Input discipline (Excel-based data collection) will be balanced with output-focused presentation formats giving clear visibility of progress, impact, and critical measures.
4 | Functional reviews and leadership reviews are distinguished: functional teams need detailed execution reviews while senior leadership focuses on EBITDA, market share, growth, and key outcomes.
5 | Existing VCP templates will be cleaned up and standardized to reduce variation in reporting quality and ensure a consistent approach across functions and teams.
6 | Teams will identify critical metrics, enabling metrics, and corresponding key themes, with clear linkage showing how each theme contributes to business performance and value creation.
7 | Dashboard and reporting capabilities were reviewed, including market-share reports, win/loss analysis, IMS data, and other sources to support metric-driven reviews.
8 | Excessive action tracking across meetings is a concern; focus shifts to a smaller set of high-priority actions, dependencies, escalations, and business-critical outcomes.
9 | Greater emphasis on monthly and quarterly impact measurement, including defining units of impact and demonstrating progress against business goals rather than tracking activity alone.
10 | The team aligned on improving governance, automating repetitive tracking where possible, strengthening ownership, and enabling leaders to spend more time on problem solving than administrative reporting.
Action Items
S. No. | Action | Owner | Due / Timing
1 | Clean up and standardize the VCP Excel template structure, tabs, and reporting format. | Aditya Jindal, Kavya Bhardwaj | Before Thursday working session
2 | Add and validate interdependency tracking mechanism across actions and workstreams in the tracker. | Aditya Jindal | Before Thursday working session
3 | Define critical metrics, enabling metrics, and corresponding impact measures for each theme/function. | Kavya Bhardwaj | Before Thursday working session
4 | Create impact-measure columns with units and progress tracking approach for business outcomes. | Aditya Jindal | Before Thursday working session
5 | Review current meeting action tracker and remove/close non-critical items; retain only critical actions, dependencies, and escalations. | Pratibha Mehta, Abhishek Chowdhary | Near-term, prior to next review cycle
6 | Evaluate use of automation/Copilot-based approach for extracting and maintaining critical meeting actions. | Abhishek Chowdhary, Kavya Bhardwaj | Short term
7 | Prepare revised review format linking key themes, metrics, progress, and impact into a concise presentation structure. | Abhishek Chowdhary, Aditya Jindal, Kavya Bhardwaj | Discussion on Thursday
8 | Schedule and conduct a working session to finalize operating cadence, reporting templates, and review standards. | Sunanda Sharma, Abhishek Chowdhary, Kavya Bhardwaj, Aditya Jindal | Thursday
9 | Review available dashboards/reports and ensure relevant market-share, win/loss, IMS, and related metrics are incorporated into VCP reviews. | Abhishek Chowdhary, Aditya Jindal | Before next VCP review
10 | Define a standardized stencil/template for root-cause analysis and KPI review to improve consistency across teams. | Sunanda Sharma, Abhishek Chowdhary | Initial draft in upcoming working session