## Slide 1: Presentation cover slide example: Vertical white logo on blue background
Service Transformation VCP Program Execution 2026-2028
MoS Strategic Execution

## Slide 2
SERVICE TRANSFORMATION VCP
Critical VCP Commitments
3
Critical commitments tracked
2
Q2 commitments below target
1
Q2 commitments met or above target
Metric | 2025 baseline | 2026 target | 2027 target | 2028 target | Q2 target | Q2 actual | Q2 signal
Service Revenue | ~€68M | €76.5M | €80.4M | €96M | €18.85M | €18.55M | Below target
Service Igm | 49.3% | 50.0% | 53.0% | 56.7% | 49.1% | 47.5% | Below target
Remote Resolution | 26.8% | Not available | Not available | >36% | 23.0% | 23.0% | On / above target
Notes: [Sources]
- CS VCP(1).xlsx, Service Transformation sheet, Critical VCP Commitments rows 92-110.

## Slide 3
COMMITMENT ENABLERS
VCP Commitment Enabling KPIs
2
Enabling KPIs with Q2 target and actual
2
Q2 commitments below target
4
KPIs with no quarterly data
KPI | 2025 baseline | 2028 target | Q2 target | Q2 actual | Q2 signal | Committed action / data note
Contract Penetration | 48.0% | 55.0% | 54.7% | 54.0% | Below target | GTM enablement + bundling at sale
CLV Revenue | €1.3M | €11M | €0.32M | €0.16M | Below target | TechMax, Hero features, upgrades
Part Harvesting Savings | Baseline | (+)€2M | Not available | Not available | No data | Circular economy + IB returns
Pricing / Value Realization | Not available | Not available | Not available | Not available | No data | Baseline, targets, committed action and quarterly data need completion
T&M Margin | Not available | Not available | Not available | Not available | No data | Baseline, targets, committed action and quarterly data need completion
Service Productivity | Not available | Not available | Not available | Not available | No data | Baseline, targets, committed action and quarterly data need completion
Notes: [Sources]
- CS VCP(1).xlsx, Service Transformation sheet, VCP Commitment Enabling KPIs rows 112-144.

## Slide 4
THEMES AND ACTIONS
Execution of Year-wise Key themes & Action Items (2026-28)
Year | Key theme | Actions | Progress / status
2026 | Profitable Growth through Customer for Life 1.9M | TechMax in Core Block (Z70/Z90); PoS for (Z10/Z30) along with Catalog; CLV - EOS Extension, FD 30X30, Becon Monitor , Win11 PSC10; Dedicated Service comercial 3 regions and Service Operations Hedcount NAR 3 regions | 62% ¦ In progress
2026 | Productivity - 1.5< + 0.2 | High Activity Sites Monitoring, FRU Rationalization; Li Phosphate Battery (Poc) ++; Sevice Productivity Funnel expansion; COO Imrovement - Labor hrs reduction, Optimised allocations, Wrong bookings | 62% ¦ In progress
2026 | Digital Service - Chat GPT AI Roadmap for Customer Experience | Chatbot based on Service Manual; PSC 10 and Connectivity improvement; RSDI - Remote software distribution and Installation -; Operational excellence - OPF, FVF, Remore rsolution | 62% ¦ In progress
2026 | Process Improvement - +0.5M | IB retension - Visibility and Win rate; T&M - Zero Sales, Process gaps; Pricing Strategy - Priority regions | 67% ¦ In progress
2027 | CLV, TechMax Propositions Expansions | Extend to FE - AVO, Elevate Upgrade, (SW High Margin); CLV Expansion - 32Inch Monitor, LiPH, Wireless Video , Onscreen Keyboard (HW) | 25% ¦ In progress
2027 | Market Share Gain deom HC- CP Penetrtion, Inside Sales, CLV GTM strategy | CP Imprvement by XX%; CLV revenue by region - DMB and Tracking; Value Proposition Workshops for Regins; GTM | 0% ¦ Not started
2027 | Profitability through Funnelled Project | Productivity Funnel - LiPh Battery, RSDI, PSC10; Warranty for consumable FRU, FRU nego, Derisking - PE CSCollaboraion; Service Delivery - CLV Margins and Contract / T&M Price Realisation DMB, Monitoring; Part Harvesting Supplier setup | 0% ¦ Not started
2028 | CLV, TechMax Propositions Expansions | Extend to FE - iApps, Duel Fluro, Pinch Zoom / Xres, QCA, QVA, 30 FPS; CLV Expansion - 15Kw to 25KW, IGZo detector, Injector Interface (HW) | 0% ¦ Not started
2028 | Profitability through Funnelled Project | Harvest- Differentiated Parts - Parts Nova; Gillardoni Derisking - PE CS colaboraion; techMax and Extended Warranty as Coreblock; Material and COO reduction - Labor cost optimisation, Allocation controls | 0% ¦ Not started
Notes: [Sources]
- CS VCP(1).xlsx, Service Transformation sheet, year-wise key theme/action blocks rows 2-90.

## Slide 5
INTERDEPENDENCIES
Cross-functional dependencies
16
Interdependency actions captured
11
Dependencies not started
0
2028 dependency rows
Function | Dependency focus | Actions | Status
Europe | Maximize Service growth | 4: HOS pricing handshake; Tech Max 2026 Roadmap definition; Tech Max 2027 Roadmap; EW/TM Core Block proposition | 100% ¦ In progress
ISC | E2E portfolio simplificaiton "TRIM" | 1: Identify Late cutomisation option which can be upgraded as FE kit to support core standard configuration | 50% ¦ In progress
Marketing | Driving launch success for Systems | 6: Dhruv: Clarity on usability claims for CS features (26WK33); Dhruv: Clarity on CS feature claims list along with substantiation plan; Dhruv: CS training plan; Dhruv: CS content for Kick-off sales training (Q4); Dhruv: CS Training; Dhruv: CS online course code creation(Q1) | 0% ¦ Not started
NAR | OIT to Rev Cycle Time Reduction | 1: Sales: drive adoption of FS- Ready configurations via meeting 0 | 50% ¦ In progress
Notes: [Sources]
- CS VCP(1).xlsx, Service Transformation sheet, Interdependencies across all function rows 173-199.

## Slide 6
INTERDEPENDENCIES
Cross-functional dependencies (cont.)
16
Interdependency actions captured
11
Dependencies not started
0
2028 dependency rows
Function | Dependency focus | Actions | Status
Quality | Reduce Product quality failures in Warranty-Part Complaints (Impact to be written); Reduce Product quality failures in Warranty-Non-Part Complaints | 4: 1.Warranty failure data and associated cost; 2. Failed Samples of MVS Internal cables from Failure Lab analysis [BEST Location from Field returned part.]; 3. Tracking of dismantled MVS-PCs at Field to be reached at Redisys (Supplier); Data collection for Non Part failure | 100% ¦ In progress

## Slide 7
RCA
RCA for red KPIs
Red metric | Q2 signal | RCA | Management follow-up
Service Revenue | €18.55M vs €18.85M (-0.30M) |  | 
Service Igm | 47.5% vs 49.1% (-1.6 pts) |  | 
Contract Penetration | 54.0% vs 54.7% (-0.7 pts) |  | 
CLV Revenue | €0.16M vs €0.32M (-0.16M) |  | 
Data readiness gap | Current evidence
Owner fields | 9/9 blank across commitment/KPI rows
Target fields | 2026 target missing 4/9; 2027 target missing 4/9; 2028 target missing 3/9
Quarterly data | 44/72 target/actual cells missing; 4 KPIs have no quarterly data
Theme tracker blanks | Impact: 31/31 ¦ Owner: 31/31 ¦ Start Date: 31/31 ¦ Theme Progress: 31/31
Notes: [Sources]
- CS VCP(1).xlsx, Service Transformation sheet, commitments rows 92-110, enabling KPI rows 112-144, theme/action rows 2-90.
- RCA wording is inferred only from red Q2 target-vs-actual signals and committed action fields in the workbook; explicit RCA fields are not populated in the source sheet.