## Slide 1: Presentation cover slide example: Vertical white logo on blue background
CS VCP Program Execution 2026-2028
MoS Strategic Execution

## Slide 2
CRITICAL VCP COMMITMENTS
Q2 target vs actual for critical KPIs
Target bars are blue. Actual bars turn green when achieved and red when below target.
Monthly VCP report | 1/6
03
Total Critical KPIs
Q2 target and actual by critical KPI
Q2 target
Actual achieved
Actual below
Chart: 
| Revenue | iGM | Remote Res.
Q2 target | 1 | 1 | 1
Q2 actual | 0.98408 | 0.96741 | 1
Monthly remarks
REVENUE
€0.30M below Q2 target. A quantified regional recovery bridge is not captured in the sheet.
SERVICE IGM
1.6 pts below Q2 target. Pricing and productivity actions need quantified contribution.
REMOTE
At the 23.0% Q2 target. Protect performance through RSDI, PSC10 and AI-enabled service.
2/3
Critical KPIs below Q2 target
Service Revenue and Service iGM need recovery action
Notes: [Sources]
- CS VCP(1).xlsx, Service Transformation sheet, Critical VCP Commitments rows 92-110.
- The clustered chart normalizes each metric to its own Q2 target because the metrics use different units.

## Slide 3
VCP COMMITMENT ENABLING KPIS
Two enabling KPIs are Q2-ready, and both are red
The chart covers Contract Penetration and CLV Revenue; four other KPI rows have no quarterly target/actual data.
Monthly VCP report | 2/6
2/6
Q2-ready KPIs
Target and actual present
2
Q2 KPIs red
Both populated KPIs miss target
4
No quarterly data
KPI rows not reviewable monthly
KPI | 2025 baseline | 2028 target | Q2 target | Q2 actual | Q2 signal | Committed action
Contract Penetration | 48.0% | 55.0% | 54.7% | 54.0% | Below target | GTM enablement + bundling at sale
CLV Revenue | €1.3M | €11M | €0.32M | €0.16M | Below target | TechMax, Hero features, upgrades
Part Harvesting Savings | Baseline | (+)€2M | Not available | Not available | No data | Circular economy + IB returns
Pricing / Value Realization | Not available | Not available | Not available | Not available | No data | Baseline, targets, committed action and quarterly data need completion
T&M Margin | Not available | Not available | Not available | Not available | No data | Baseline, targets, committed action and quarterly data need completion
Service Productivity | Not available | Not available | Not available | Not available | No data | Baseline, targets, committed action and quarterly data need completion
Notes: [Sources]
- CS VCP(1).xlsx, Service Transformation sheet, VCP Commitment Enabling KPIs rows 112-144.
- KPI rows without Q2 target and actual values are excluded from the chart and shown as data gaps.

## Slide 4
THEMES AND ACTIONS
Year-wise themes connect execution to the 2026-28 runway
Monthly VCP report | 3/6
Year | Key theme | Actions | Progress / status
2026 | Profitable Growth through Customer for Life 1.9M | TechMax in Core Block (Z70/Z90); PoS for (Z10/Z30) along with Catalog; CLV - EOS Extension, FD 30X30, Becon Monitor , Win11 PSC10; Dedicated Service commercial 3 regions and Service Operations Headcount NAR 3 regions | 62% ¦ In progress
2026 | Productivity - 1.5< + 0.2 | High Activity Sites Monitoring, FRU Rationalization; Li Phosphate Battery (Poc) ++; Service Productivity Funnel expansion; COO Improvement - Labor hrs reduction, Optimised allocations, Wrong bookings | 62% ¦ In progress
2026 | Digital Service - ChatGPT AI Roadmap for Customer Experience | Chatbot based on Service Manual; PSC 10 and Connectivity improvement; RSDI - Remote software distribution and Installation -; Operational excellence - OPF, FVF, Remote resolution | 62% ¦ In progress
2026 | Process Improvement - +0.5M | IB retension - Visibility and Win rate; T&M - Zero Sales, Process gaps; Pricing Strategy - Priority regions | 67% ¦ In progress
2027 | CLV, TechMax Propositions Expansions | Extend to FE - AVO, Elevate Upgrade, (SW High Margin); CLV Expansion - 32Inch Monitor, LiPH, Wireless Video , Onscreen Keyboard (HW) | 25% ¦ In progress
2027 | Market Share Gain demo HC- CP Penetration, Inside Sales, CLV GTM strategy | CP Imprvement by XX%; CLV revenue by region - DMB and Tracking; Value Proposition Workshops for Regions; GTM | 0% ¦ Not started
2027 | Profitability through Funnelled Project | Productivity Funnel - LiPh Battery, RSDI, PSC10; Warranty for consumable FRU, FRU nego, Derisking - PE CSCollaboraion; Service Delivery - CLV Margins and Contract / T&M Price Realisation DMB, Monitoring; Part Harvesting Supplier setup | 0% ¦ Not started
2028 | CLV, TechMax Propositions Expansions | Extend to FE - iApps, Dual Fluro, Pinch Zoom / Xres, QCA, QVA, 30 FPS; CLV Expansion - 15Kw to 25KW, IGZo detector, Injector Interface (HW) | 0% ¦ Not started
2028 | Profitability through Funnelled Project | Harvest- Differentiated Parts - Parts Nova; Gillardoni Derisking - PE CS collaboration; techMax and Extended Warranty as Coreblock; Material and COO reduction - Labor cost optimisation, Allocation controls | 0% ¦ Not started
Notes: [Sources]
- CS VCP(1).xlsx, Service Transformation sheet, key theme/action blocks rows 2-90.

## Slide 5
INTERDEPENDENCIES
Cross-functional actions
Monthly VCP report | 4/6
16
Dependency actions
Across five functions
11
Not started
Main execution risk
Leadership focus
Marketing and Quality hold 9 of the 11 not-started actions.
Dependency action register (one action per line)
2028: no actions captured
YEAR
FUNCTION
ACTION
STATUS
2026
ISC
Identify Late customisation option which can be upgraded as FE kit to support core standard configuration
In progress
2026
Quality
1.Warranty failure data and associated cost
Completed
2026
Quality
2. Failed Samples of MVS Internal cables from Failure Lab analysis [BEST Location from Field returned part.]
Not started
2026
Quality
3. Tracking of dismantled MVS-PCs at Field to be reached at Redisys (Supplier)
Not started
2026
Quality
Data collection for Non Part failure
Not started
2026
Marketing
Dhruv: Clarity on usability claims for CS features (26WK33)
Not started
2026
Marketing
Dhruv: Clarity on CS feature claims list along with substantiation plan
Not started
2026
Marketing
Dhruv: CS training plan
Not started
2026
Marketing
Dhruv: CS content for Kick-off sales training (Q4)
Not started
2026
NAR
Sales: drive adoption of FS- Ready configurations via meeting 0
In progress
2026
Europe
HOS pricing handshake
Completed
2026
Europe
Tech Max 2026 Roadmap definition
Completed
2027
Marketing
Dhruv: CS Training
Not started
2027
Marketing
Dhruv: CS online course code creation(Q1)
Not started
2027
Europe
Tech Max 2027 Roadmap
Not started
2027
Europe
EW/TM Core Block proposition
Not started
Source: CS VCP(1).xlsx, Service Transformation, Interdependencies across all function rows 173-199.
Notes: [Sources]
- CS VCP(1).xlsx, Service Transformation sheet, Interdependencies across all function rows 173-199.

## Slide 6
VCP IMPACT LINKAGE
How service KPIs translate into VCP value
The workbook quantifies Sales and Adjusted EBITA trajectories; Market Share remains a directional impact without a stated target.
Monthly VCP report | 5/6
€96M
2028 VCP Sales trajectory
From €77.4M in 2026
€43.2M
2028 Adjusted EBITA trajectory
From €30.6M in 2026
Not quantified
Market Share target
Impact path is referenced through GTM, portfolio and contract growth themes
Impact driver map
GROWTH ENGINE
Enabling KPIs
Contract Pen. 99% attainment; CLV Revenue 50%
Service Revenue
98% of Q2 target; gap €0.30M
VCP Sales
€77.4M in 2026 to €96M in 2028
MARGIN ENGINE
Operating levers
Remote Resolution at target; pricing/productivity data incomplete
Service iGM
97% of Q2 target; gap 1.6 pts
Adjusted EBITA
€30.6M in 2026 to €43.2M in 2028
SHARE ENGINE
Portfolio + GTM
TechMax, hero features, upgrades, bundling and inside-sales support
Adoption
Contract and CLV indicators are below Q2 target
Market Share
Directionally positive; no quantified target in sheet
VCP outcome trajectory (€M)
Chart: 
| 2026 | 2027 | 2028
Sales | 77.4 | 80.4 | 96
Adj. EBITA | 30.6 | 34.17 | 43.2
2028 iGM plan: 56.7%
Notes: [Sources]
- CS VCP(1).xlsx, Service Transformation sheet, VCP impact rows 151-169 and KPI sections rows 92-144.
- Market Share is shown as a directional link only because no target or actual is present in the workbook.

## Slide 7
RCA AND SHEET PERFORMANCE
Q2 red KPIs need documented root causes
RCA is not captured in the sheet, and data gaps also limit the monthly review.
Monthly VCP report | 6/6
RCA follow-up for Q2 red KPIs
Service Revenue
-0.30M
RCA status: Not captured; Contract Penetration and CLV Revenue are also below target.
Management action: Build a region-level bridge across CLV, contracts and PoS bundling.
Service iGM
-1.6 %
RCA status: Not captured; Pricing, T&M Margin and Productivity KPI data are blank.
Management action: Quantify the pricing/productivity bridge and assign accountable owners.
Contract Penetration
-0.7 %
RCA status: Not captured; GTM enablement and bundling at sale are the stated levers.
Management action: Document region conversion blockers and recovery actions.
CLV Revenue
-0.16M
RCA status: Not captured; TechMax, hero features and upgrades are named, but the miss is unexplained.
Management action: Reconcile the CLV pipeline to Q3/Q4 targets and close risks.
Sheet performance report
44/72
Quarterly target / actual cells blank
39% populated
67%
Critical qtr data
Cells populated
25%
Enabling qtr data
Cells populated
Missing core KPI fields
Owner
9/9
Baseline (2025)
4/9
Target 2026
4/9
Target 2027
4/9
Target 2028
3/9
Committed actions
3/9
5 fully empty theme-tracker columns
Impact, Owner, Start Date, Theme Progress and Unit. Planned Completion is blank in 25/31 rows; Action Progress in 14/31.